## Summary
Job Portal — Test Plan
Project | Job Portal (COSC 360 Team 21 — W25/26)
Stack | MERN (MongoDB, Express, React 18, Node.js) + Docker
Date | 2026-03-27
Frameworks | Backend: Vitest + Supertest + mongodb-memory-server ¦ Frontend: Vitest + RTL ¦ E2E: Playwright (Chromium)
Layer | Total | Existing | TODO | % Done
Unit — Backend | 38 | 27 | 11 | 71%
Unit — Frontend | 19 | 6 | 13 | 32%
Integration | 17 | 5 | 12 | 29%
E2E | 26 | 4 | 22 | 15%
TOTAL | 100 | 42 | 58 | 42%
LEGEND
Layer
Unit-BE | Backend endpoint tests (Vitest + Supertest + in-memory DB)
Unit-FE | Frontend component tests (Vitest + React Testing Library)
Integration | Multi-step API flows; verifies state carries between requests
E2E | Full browser automation against the running Docker stack (Playwright)
Test Type
Smoke | Minimal 'is it alive' check — run first on every build
Happy Path | Valid input, expected success — covers the main use case
Negative | Invalid input or wrong state — expects an error response
Validation | Field format / length / required-field rules
Security | Authentication and authorisation checks (401 / 403)
Contract | Verifies request shape or response schema between layers
Flow | Multi-step sequence verifying state carries between steps
Status
Existing | Test is already written and passing in CI
TODO | Test is planned but not yet implemented

## Test Plan
ID | Layer | Test Type | Feature | Description | File Path | Status | Priority | Assignee | Result | Notes
UT-B-001 | Unit-BE | Smoke | Health | GET /api/health returns 200 { status: 'ok' } | backend/src/__tests__/health.test.js | Existing | High
UT-B-002 | Unit-BE | Happy Path | Auth / Register | 201 + token + user object on valid input | backend/src/__tests__/auth.test.js | Existing | High
UT-B-003 | Unit-BE | Happy Path | Auth / Register | 201 with employer role when role=employer is specified | backend/src/__tests__/auth.test.js | Existing | High
UT-B-004 | Unit-BE | Negative | Auth / Register | 400 when email is already registered | backend/src/__tests__/auth.test.js | Existing | High
UT-B-005 | Unit-BE | Validation | Auth / Register | 400 when name field is missing | backend/src/__tests__/auth.test.js | Existing | Medium
UT-B-006 | Unit-BE | Validation | Auth / Register | 400 when email format is invalid | backend/src/__tests__/auth.test.js | Existing | Medium
UT-B-007 | Unit-BE | Validation | Auth / Register | 400 when password is shorter than 6 characters | backend/src/__tests__/auth.test.js | Existing | Medium |  |  | Min length = 6
UT-B-008 | Unit-BE | Happy Path | Auth / Login | 200 + JWT token on valid credentials | backend/src/__tests__/auth.test.js | Existing | High
UT-B-009 | Unit-BE | Negative | Auth / Login | 401 when password is incorrect | backend/src/__tests__/auth.test.js | Existing | High
UT-B-010 | Unit-BE | Negative | Auth / Login | 401 when email does not exist | backend/src/__tests__/auth.test.js | Existing | High
UT-B-011 | Unit-BE | Validation | Auth / Login | 400 when email field is missing from body | backend/src/__tests__/auth.test.js | Existing | Medium
UT-B-012 | Unit-BE | Happy Path | Auth / Me | 200 + user object for valid Bearer token | backend/src/__tests__/auth.test.js | Existing | High
UT-B-013 | Unit-BE | Security | Auth / Me | 401 when Authorization header is absent | backend/src/__tests__/auth.test.js | Existing | High
UT-B-014 | Unit-BE | Security | Auth / Me | 401 with a malformed / tampered JWT | backend/src/__tests__/auth.test.js | Existing | High
UT-B-015 | Unit-BE | Security | Auth / Me | 401 with 'Bearer ' header present but token value missing | backend/src/__tests__/auth.test.js | Existing | Medium |  |  | Edge case
UT-B-016 | Unit-BE | Happy Path | Jobs / List | Paginated list with default page=1, limit=10 | backend/src/__tests__/jobs.test.js | Existing | High |  |  | Checks pagination metadata
UT-B-017 | Unit-BE | Happy Path | Jobs / List | Paginated list with explicit page=2, limit=5 | backend/src/__tests__/jobs.test.js | Existing | High
UT-B-018 | Unit-BE | Validation | Jobs / List | 400 for invalid pagination params (page=0, limit=500) | backend/src/__tests__/jobs.test.js | Existing | Medium
UT-B-019 | Unit-BE | Happy Path | Jobs / Create | 201 job created when requester is authenticated employer | backend/src/__tests__/jobs.test.js | Existing | High
UT-B-020 | Unit-BE | Security | Jobs / Create | 401 when Authorization token is missing | backend/src/__tests__/jobs.test.js | Existing | High
UT-B-021 | Unit-BE | Security | Jobs / Create | 403 when requester role is jobseeker | backend/src/__tests__/jobs.test.js | Existing | High |  |  | Role guard
UT-B-022 | Unit-BE | Happy Path | Jobs / Update | 200 updates job when requester is the owner employer | backend/src/__tests__/jobs.test.js | Existing | High
UT-B-023 | Unit-BE | Security | Jobs / Update | 403 when a different employer (non-owner) tries to update | backend/src/__tests__/jobs.test.js | Existing | High
UT-B-024 | Unit-BE | Validation | Jobs / Update | 400 for invalid MongoDB ObjectId format in URL param | backend/src/__tests__/jobs.test.js | Existing | Medium
UT-B-025 | Unit-BE | Happy Path | Jobs / Delete | 200 deletes job when requester is the owner employer | backend/src/__tests__/jobs.test.js | Existing | High
UT-B-026 | Unit-BE | Security | Jobs / Delete | 403 when a different employer (non-owner) tries to delete | backend/src/__tests__/jobs.test.js | Existing | High
UT-B-027 | Unit-BE | Validation | Jobs / Delete | 400 for invalid MongoDB ObjectId format in URL param | backend/src/__tests__/jobs.test.js | Existing | Medium
UT-B-028 | Unit-BE | Happy Path | Jobs / Search | Keyword filter returns only jobs matching title/description | backend/src/__tests__/jobs.test.js | TODO | High |  |  | Requires search impl
UT-B-029 | Unit-BE | Happy Path | Jobs / Search | Location filter returns only jobs matching location | backend/src/__tests__/jobs.test.js | TODO | High
UT-B-030 | Unit-BE | Happy Path | Jobs / Search | Job type filter returns only full-time or part-time jobs | backend/src/__tests__/jobs.test.js | TODO | Medium
UT-B-031 | Unit-BE | Happy Path | Jobs / Detail | 200 returns single job object for valid ID | backend/src/__tests__/jobs.test.js | TODO | High |  |  | GET /api/jobs/:id
UT-B-032 | Unit-BE | Negative | Jobs / Detail | 404 when job ID does not exist in database | backend/src/__tests__/jobs.test.js | TODO | High
UT-B-033 | Unit-BE | Happy Path | Applications | 201 when jobseeker submits a valid application | backend/src/__tests__/applications.test.js | TODO | High |  |  | New feature
UT-B-034 | Unit-BE | Negative | Applications | 409 when jobseeker applies to the same job a second time | backend/src/__tests__/applications.test.js | TODO | High |  |  | Duplicate guard
UT-B-035 | Unit-BE | Security | Applications | 403 when employer attempts to submit an application | backend/src/__tests__/applications.test.js | TODO | High |  |  | Role guard
UT-B-036 | Unit-BE | Happy Path | Applications | 200 employer retrieves applicant list for their own job | backend/src/__tests__/applications.test.js | TODO | Medium
UT-B-037 | Unit-BE | Happy Path | User Profile | 200 user updates their own name / bio | backend/src/__tests__/user.test.js | TODO | Medium
UT-B-038 | Unit-BE | Validation | User Profile | 400 when disallowed fields (role, email) are included | backend/src/__tests__/user.test.js | TODO | Medium
UT-F-001 | Unit-FE | Smoke | App / Routing | App component mounts without throwing | frontend/src/__tests__/App.test.jsx | Existing | High
UT-F-002 | Unit-FE | Smoke | App / Routing | Home page renders 'Job Portal' heading | frontend/src/__tests__/App.test.jsx | Existing | High
UT-F-003 | Unit-FE | Smoke | App / Routing | Home page shows Login and Register nav links | frontend/src/__tests__/App.test.jsx | Existing | High
UT-F-004 | Unit-FE | Happy Path | App / Routing | Navigating to /login renders the Login page | frontend/src/__tests__/App.test.jsx | Existing | High
UT-F-005 | Unit-FE | Happy Path | App / Routing | Navigating to /register renders the Register page | frontend/src/__tests__/App.test.jsx | Existing | High
UT-F-006 | Unit-FE | Happy Path | App / Routing | Login page contains a back-link that points to '/' | frontend/src/__tests__/App.test.jsx | Existing | Low |  |  | Low value — nav only
UT-F-007 | Unit-FE | Contract | Login Form | Submitting valid credentials fires POST /api/auth/login with correct body shape | frontend/src/__tests__/Login.test.jsx | TODO | High |  |  | Use MSW to intercept
UT-F-008 | Unit-FE | Negative | Login Form | Inline error message appears when API returns 401 | frontend/src/__tests__/Login.test.jsx | TODO | High
UT-F-009 | Unit-FE | Happy Path | Login Form | Submit button is disabled while the request is in-flight | frontend/src/__tests__/Login.test.jsx | TODO | Medium |  |  | Loading state
UT-F-010 | Unit-FE | Contract | Register Form | Submitting valid data fires POST /api/auth/register with correct body shape | frontend/src/__tests__/Register.test.jsx | TODO | High
UT-F-011 | Unit-FE | Validation | Register Form | Client-side error shown when passwords do not match | frontend/src/__tests__/Register.test.jsx | TODO | High |  |  | Before API call
UT-F-012 | Unit-FE | Happy Path | Job Listings | Renders a card for each job returned by the API | frontend/src/__tests__/JobListings.test.jsx | TODO | High |  |  | Mock API response
UT-F-013 | Unit-FE | Negative | Job Listings | Empty-state message displayed when API returns 0 jobs | frontend/src/__tests__/JobListings.test.jsx | TODO | Medium
UT-F-014 | Unit-FE | Contract | Job Search | Typing in search box and submitting fires GET /api/jobs?keyword=... | frontend/src/__tests__/JobSearch.test.jsx | TODO | High
UT-F-015 | Unit-FE | Happy Path | Job Search | Location dropdown selection appends &location= to query | frontend/src/__tests__/JobSearch.test.jsx | TODO | Medium
UT-F-016 | Unit-FE | Happy Path | Auth Context | JWT token is persisted to localStorage after successful login | frontend/src/__tests__/AuthContext.test.jsx | TODO | High
UT-F-017 | Unit-FE | Happy Path | Auth Context | Logout clears token from localStorage and context | frontend/src/__tests__/AuthContext.test.jsx | TODO | High
UT-F-018 | Unit-FE | Security | Protected Route | Unauthenticated user is redirected to /login | frontend/src/__tests__/ProtectedRoute.test.jsx | TODO | High |  |  | Route guard
UT-F-019 | Unit-FE | Security | Protected Route | Employer-only route blocks a logged-in jobseeker | frontend/src/__tests__/ProtectedRoute.test.jsx | TODO | High |  |  | Role guard
IT-001 | Integration | Flow | Auth | Register → Login → GetMe: token from register is valid through full lifecycle | backend/src/__tests__/auth.test.js | Existing | High |  |  | Lifecycle flow
IT-002 | Integration | Security | Auth | Expired JWT returns 401 on any protected route | backend/src/__tests__/auth.test.js | TODO | High |  |  | Set jwt expiry to 1s in test
IT-003 | Integration | Flow | Jobs | Employer registers → creates job → retrieves job by ID | backend/src/__tests__/jobs.test.js | Existing | High
IT-004 | Integration | Flow | Jobs | Create job → update job → verify all changed fields persist | backend/src/__tests__/jobs.test.js | Existing | High
IT-005 | Integration | Flow | Jobs | Create job → delete job → GET confirms 404 | backend/src/__tests__/jobs.test.js | Existing | High
IT-006 | Integration | Happy Path | Jobs | Seed 12 jobs → paginated list returns correct subset and total count | backend/src/__tests__/jobs.test.js | Existing | High |  |  | Pagination integrity
IT-007 | Integration | Happy Path | Jobs / Search | Seed jobs with varied titles → keyword search returns only matches | backend/src/__tests__/jobs.test.js | TODO | High |  |  | Requires search impl
IT-008 | Integration | Happy Path | Jobs / Search | Seed jobs with varied locations → location filter returns only matches | backend/src/__tests__/jobs.test.js | TODO | High
IT-009 | Integration | Happy Path | Jobs / Search | Combined keyword + location filter reduces result set correctly | backend/src/__tests__/jobs.test.js | TODO | Medium
IT-010 | Integration | Flow | Applications | Jobseeker registers → applies to job → application appears in list | backend/src/__tests__/applications.test.js | TODO | High |  |  | New feature
IT-011 | Integration | Negative | Applications | Jobseeker cannot apply to the same job twice (idempotency) | backend/src/__tests__/applications.test.js | TODO | High
IT-012 | Integration | Security | Applications | Employer cannot see applicants for another employer's job | backend/src/__tests__/applications.test.js | TODO | High |  |  | Data isolation
IT-013 | Integration | Flow | Applications | Employer closes application window → job marked closed in DB | backend/src/__tests__/applications.test.js | TODO | Medium
IT-014 | Integration | Flow | Data Integrity | Deleting a job cascades to remove all its applications | backend/src/__tests__/jobs.test.js | TODO | High |  |  | Referential integrity
IT-015 | Integration | Contract | API Contract | Login form POSTs { email, password } — no extra or missing fields | frontend/src/__tests__/Login.test.jsx | TODO | Medium |  |  | MSW or real backend
IT-016 | Integration | Contract | API Contract | Job listings page requests GET /api/jobs with correct pagination params | frontend/src/__tests__/JobListings.test.jsx | TODO | Medium
IT-017 | Integration | Contract | API Contract | Job search form fires GET /api/jobs?keyword=&location= on submit | frontend/src/__tests__/JobSearch.test.jsx | TODO | High
E2E-001 | E2E | Smoke | Home Page | Page loads and 'Job Portal' heading is visible | e2e/tests/auth.spec.js | Existing | High
E2E-002 | E2E | Smoke | Home Page | Login and Register navigation links are visible | e2e/tests/auth.spec.js | Existing | High
E2E-003 | E2E | Happy Path | Navigation | Clicking Login navigates browser to /login | e2e/tests/auth.spec.js | Existing | High
E2E-004 | E2E | Happy Path | Navigation | Clicking Register navigates browser to /register | e2e/tests/auth.spec.js | Existing | High
E2E-005 | E2E | Happy Path | Register Flow | User fills form → submits → lands on dashboard | e2e/tests/auth.spec.js | TODO | High
E2E-006 | E2E | Negative | Register Flow | Duplicate email submission shows inline error message | e2e/tests/auth.spec.js | TODO | High
E2E-007 | E2E | Validation | Register Flow | Short password triggers validation error before API call | e2e/tests/auth.spec.js | TODO | Medium
E2E-008 | E2E | Happy Path | Login Flow | Valid credentials → user is redirected to dashboard | e2e/tests/auth.spec.js | TODO | High
E2E-009 | E2E | Negative | Login Flow | Wrong password shows error message on login page | e2e/tests/auth.spec.js | TODO | High
E2E-010 | E2E | Negative | Login Flow | Non-existent email shows error message on login page | e2e/tests/auth.spec.js | TODO | High
E2E-011 | E2E | Happy Path | Login Flow | Logged-in user sees Logout button in nav bar | e2e/tests/auth.spec.js | TODO | Medium |  |  | Session state
E2E-012 | E2E | Happy Path | Logout Flow | Clicking Logout clears session and redirects to home | e2e/tests/auth.spec.js | TODO | High
E2E-013 | E2E | Happy Path | Job Listings | Unauthenticated user can browse the job listings page | e2e/tests/jobs.spec.js | TODO | High |  |  | Public route
E2E-014 | E2E | Happy Path | Job Search | Keyword search filters displayed job cards to matches only | e2e/tests/jobs.spec.js | TODO | High |  |  | Core feature
E2E-015 | E2E | Happy Path | Job Search | Location filter narrows displayed job cards | e2e/tests/jobs.spec.js | TODO | High
E2E-016 | E2E | Happy Path | Job Search | Clearing search inputs restores the full job list | e2e/tests/jobs.spec.js | TODO | Medium
E2E-017 | E2E | Happy Path | Job Detail | Clicking a job card opens the job detail page with full info | e2e/tests/jobs.spec.js | TODO | High
E2E-018 | E2E | Flow | Employer | Employer logs in → posts new job → job appears in public listings | e2e/tests/employer.spec.js | TODO | High |  |  | Core feature
E2E-019 | E2E | Flow | Employer | Employer edits job posting → updated fields visible on listing | e2e/tests/employer.spec.js | TODO | High
E2E-020 | E2E | Flow | Employer | Employer deletes job → listing no longer appears | e2e/tests/employer.spec.js | TODO | High
E2E-021 | E2E | Happy Path | Employer | Employer views applicant list for their job | e2e/tests/employer.spec.js | TODO | Medium
E2E-022 | E2E | Flow | Jobseeker | Jobseeker logs in → applies to job → confirmation shown | e2e/tests/jobseeker.spec.js | TODO | High |  |  | Core feature
E2E-023 | E2E | Negative | Jobseeker | Applying to the same job twice shows 'already applied' message | e2e/tests/jobseeker.spec.js | TODO | High |  |  | Duplicate guard
E2E-024 | E2E | Happy Path | Jobseeker | Jobseeker dashboard lists all submitted applications | e2e/tests/jobseeker.spec.js | TODO | Medium
E2E-025 | E2E | Security | Access Control | Jobseeker cannot navigate to the employer job-post page | e2e/tests/access.spec.js | TODO | High |  |  | Role guard
E2E-026 | E2E | Security | Access Control | Unauthenticated user visiting a protected route is redirected to /login | e2e/tests/access.spec.js | TODO | High |  |  | Auth guard